## MAP
Mutual Action Plan
| Success Criteria for Partnership |  | Notes
Most important payoff #1
Most important payoff #2
Most important payoff #3
Most important payoff #4
| Key Stakeholders |  | Roles
Buyer #1
Buyer #2
Buyer #3
Your Company #1
Your Company #2
Your Company #3
| MILESTONES |  | Days | Start | End | OWNER
| Complete? | Priorities | 3 | 2022-01-01 | 2022-01-04 | Responsible?
| FALSE | Problem Statement
| FALSE | Business Case Built
| Complete? | Proof of Value | 3 | 2022-01-04 | 2022-01-07 | Responsible?
| FALSE | Share demo data
| FALSE | Calculate ROI
| Complete? | Executive Buy-In | 25 | 2022-01-07 | 2022-02-01 | Responsible?
| FALSE | Review data from POC
| FALSE | Share final report
| Complete? | Security | 2 | 2022-02-01 | 2022-02-03 | Responsible?
| FALSE | Compliance audit
| FALSE | Documentation submitted
| Complete? | Contracting | 20 | 2022-02-03 | 2022-03-03 | Responsible?
| FALSE | Pricing set
| FALSE | Legal approval
| FALSE | Finance approval
| FALSE | Contract executed
| Complete? | Kickoff Setup | 20 |  | 2022-03-31 | Responsible?
| FALSE | Step 1
| FALSE | Step 2
| FALSE | Step 3
| IMPLEMENTATION DATE |  | 6 |  | 2022-04-08
| ON TRACK | Check In | 20 |  | 2022-05-06 | Responsible?
| FALSE | Success milestone #1
| FALSE | Success milestone #2
| FALSE | Success milestone #3
Formulas:
End = [Start]+[Days]
End = WORKDAY(F31,[Days])